Project Implementation Plan

| PROJECT TITLE: Pricing Overhaul |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE: Improve profitability by increasing starting gross margins |  |  |  |  |
| ACTIONS | Est. Hours | People Involved | Target Date | Actual Date |
| Collect current prices & profit margins | .5 | Assistant | 1/20 |  |
| Collect competitor info | 2 | Assistant | 1/23 |  |
| Interview key customers | 3 | Self, VP Sales | 2/5 |  |
| Analyze research | 2 | Self | 2/15 |  |
| Organize & lead product development / sales round table | 1 | Self | 2/25 |  |
| Get key customer feedback | 3 | VP Sales | 3/15 |  |
| Organize & lead sales / marketinground table | 1 | Self | 3/25 |  |
| Finalize new product specs & pricing | 1 | VP Product Development | 3/30 |  |
| Get final approvals | 1 | Self, CFO, Pres. | 4/5 |  |
| Present to the sales team | 2 | Self, VP Sales | 4/20 |  |
| Due Date: 5/1 |  |  |  |  |

Project Implementation Plan

| PROJECT TITLE: |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE: |  |  |  |  |
| ACTIONS | Est. Hours | People Involved | Target Date | Actual Date |
| Due Date: |  |  |  |  |